## Sheet1
SL NO | MODULE | STATUS | COMMENT | clarification
1 | Customer Enrollment
| OTP/Debit card verification for user registration | To be done | To be integrated with card system | Requirement to be identified
| Customer Enrolment/Onboarding -- paperless | Done
| eKYC and Aadhar Linking | To be done | To be integrated with AADHAR system
| Forgot Access Code | open | Requirement to be identified
3 | Accounts summary
| Savings | Done
| Loans | Done
| Deposits | Done
| Accounts summary | Done
4 | Dashboard
| Customer Dashboard | Done
| Personalized Dashboard with Visualization | Done
5 | Transaction Management
| Third Party Fund Transfer --Hot payment,Schedule, recurring | Done
| Transactions within the bank --Hot payment,Schedule, recurring | Done
| Split Bills | To be done | Requirement to be identified
| Batch for schedule and recurring | To be done | Requirement to be identified
| Beneficiary Manitainence -- picture and list view | To be done | Requirement to be identified
| Limits | To be done | Requirement to be identified
6 | Mails | Not Done
7 | User Profile
| Change password | Done
| Update communication details with geo tagging | Done
| Authentication and authoriazation changes | Done
| Limits change by user | To be done | Requirement to be identified
8 | Other Retail Modules | ON HOLD
Insurance
Mutual Funds display
Tax Payments
10 | Agent/BC/RM Banking -- Digi on wheels
| Unified View - Common Login for Customer and Agent | Done | Requirement to be identified
| Seamless usability across devices | Done | Requirement to be identified
| Online registration for customer and agent | To be done | Requirement to be identified
| Comprehensive Dashboard View for Customer | Done | Requirement to be identified
| Comprehensive Dashboard View for Agent | Done | Requirement to be identified
| Due Payments by Online | To be done | Requirement to be identified
| Due Payments by Offline | To be done | Requirement to be identified
| Aadhar Verification using biometric/OTP | To be done | Requirement to be identified
| Chat Service Integration | To be done | Requirement to be identified
| Geo-Tagging of Customer and Agent Locations | Done | Requirement to be identified
| EMI Calculator | To be done | Requirement to be identified
| e-KYC, CIBIL Schore Check | To be done | Requirement to be identified
| Loan Application Status Tracking | Done | Requirement to be identified
| Loan Collections/Payments | To be done | Requirement to be identified
| Customer Onboarding | Done | Requirement to be identified
| Loans Account Opening Initiation | To be done | Requirement to be identified
| Loans Disbursal Initiation | To be done | Requirement to be identified
| Other Collections/Payments | To be done | Requirement to be identified
| Cash Deposits/Withdrawal online offline | To be done | Requirement to be identified
| Term Deposit Account Opening | To be done | Requirement to be identified
| Nearby Customer Locations in Dealers Dashboard | To be done | Requirement to be identified
-
11 | Personal Finance Management (Aggregation)
| Account aggregration from all financial service providers | To be done
| Holistic View of all Accounts | To be done
| Spending Analysis | To be done
| Visualizations for Earnings Vs Spendings | To be done
| Budgeting | To be done
| Adding Personal Accountings | To be done
| Alerts for burst of budgets | To be done
| Categorization | To be done
| Saving Goals | To be done
| Seamless usability across devices | To be done
12 | Service Request
| Cheque book request | Done
| Block Debit Card | Done | Stub
| Stop Cheque | To be done
| FD Opening | Done | Stub
| RD Opening | Done | Stub
| Loan Account Opening | Done | Stub
13 | Bill Payment
| Payment Billers only | To be done | Requirement to be identified
| Presentment Billers | To be done | Requirement to be identified
14 | Corporate Modules
| Transaction/Salary File upload | To be done
| Trade Finance | To be done | Requirement to be identified
| Liquidity Management | On Hold | Requirement to be identified
| Corporate Functionality | To be done | Requirement to be identified
15 | Additional Features
| Location based access control | Done
| Artificial Intelligence & analytics | On Hold
| Pensioner verification -- life certificate -- video authenticaiton | On Hold
16 | Admin | Done
| Corporate administration | Done
| Retail Administration | Done
| Property Maintenance | Done
| Admin Maintenance | Done
| General Services | Done
| Transaction Maintenance | Done
| Testing Phase | To be done
| Integration Testing | To be done
| Security and Penetration Testing | To be done
| Audit by external team | To be done
MOBILE
1 | Login
| Retail, Corporate, Agent | To be done | To be done
|  | To be done | To be done
|  | Done | Done
2 | Retail User
| Dashboard | Done | Except getting data of chart everything is done
| My profile | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
| Fund Transfer | Done | Api connectivity is done, but getting some data mismatch error
| Beneficiary | Done | Done
|  | Done | Done
|  | Done | Done
| Transactions | To be done | To be done
| Quick Payment | Done | Api connectivity is to be done
| Book Agent | Done | Api connectivity is to be done
| Accoutn summary | Done | Done
| Loan Account | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
| Deposit Account | Done | Api connectivity is to be done
|  | To be done | To be done
|  | To be done | To be done
| Bill payment | To be done | To be done
| General Services | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
| Notifications | Done | Done
| Multi currency | To be done | To be done
3 | Corporate User
| Dash board | Done | Api connectivity is to be done
| Quick Payment | Done | Api connectivity is to be done
| Account List | Done | Api connectivity is to be done
| Trade Finance | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
| Corporate Maintenance | Done | Api connectivity is to be done
|  | Done | Api connectivity is to be done
| Notifications | Done | Api connectivity is to be done
With respect to Web, rest of the screens to be designed and developed
4 | Agent User
| Dash board | Done | Api connectivity is to be done
| Pending application for verification | Done | Done
| Notifications | Done | Api connectivity is to be done
| Video verification | Done | Done
With respect to Web, rest of the screens to be designed and developed